## Sheet1
DATE | TASKS | SUBGROUPS | MEETINGS | NOTES
14/02/2022 | Collecting Ideas, Discussion On Project Building Strategies | 1]FRONT-END: { Ketan A, Hemalata , Dhruvi , Varshini , Bindu, Naresh} | 1] Morning_Meeting: (9:15 AM TO 10:30 AM) 2] Evening_Meeting: (5.30 PM TO 6:00 PM) | Referred Some Popular Hospital Sites, Created Rough Project Road Map and Group Division
2]BACK-END: {Maneesha, Geetha, Aravind, MalkiReddy, Navaru B}
15/02/2022 | {Frontend Co-Leader & Backend Co-Leader}Frontend and Backend Development | 1]FRONT-END: { Ketan A: Admin Login, Hemalata:Home Page , Dhruvi: Doctor Login , Varshini: About Us , Bindu: Appointment, Naresh: Feedback} | 1] Morning_Meeting: (9:30 AM TO 10:25 AM) 2] Evening_Meeting: (6.10 PM TO 6:55 PM) | Analyzing individual work and suggestions for it.
2]BACK-END: {Maneesha: Patient, Geetha:Invoice, Aravind:Admin, MalkiReddy:Doctor, Navaru B:Feedback}
16/02/2022 | Component Development and Backend Corrections and Development | 1]FRONT-END: { Ketan A: Admin Login, Hemalata:Home Page , Dhruvi: Doctor Login , Varshini: About Us , Bindu: Appointment, Naresh: Feedback} | 1] Morning_Meeting: (9:30 AM TO 10:25 AM) 2] Evening_Meeting: (6.10 PM TO 6:55 PM) | Bit Lagged in Frontend Part and Backend is going as Expected {Almost 45% Backend Done.}
2]BACK-END: {Maneesha: Patient, Geetha:Invoice, Aravind:Admin, MalkiReddy:Doctor, Navaru B:Feedback}
17/02/2022 | Component Linking and Backend Integration and Finalize Landing Page | 1]FRONT-END: { Ketan A: Admin SignUp, Hemalata: Patient , Dhruvi: Doctor SignUp , Varshini: About Us , Bindu: Appointment, Naresh: Feedback} | 1] Morning_Meeting: (9:30 AM TO 10:40 AM) 2] Evening_Meeting: (6.10 PM TO 6:55 PM) | Done With Landing Page as well as Admin Login and some components for other parts, Backend{ 60% Done few upgradation and changes required}
2]BACK-END: {Maneesha: Appointment, Geetha:Discharge, Aravind:Admin, MalkiReddy:Doctor, Navaru B:Feedback}
18/02/2022 | Bit Behind for Frontend and Backend Integration | 1]FRONT-END: { Ketan A: Admin , Hemalata: Patient SignUp, Dhruvi: Doctor SignUp, Varshini: About Us , Bindu: Appointment, Naresh: Feedback} | 1] Morning_Meeting: (9:30 AM TO 10:25 AM) 2] Evening_Meeting: (6.30 PM TO 7:55 PM) | Frontend {50% Done With Admin SignUp ,Doctor Login and Patient Login Part }. Backend {70% Done with Junit and Done with Unit Testing}
2]BACK-END: {Maneesha: Appointment,Unit testing,Junit Geetha:Discharge, Aravind:Admin, MalkiReddy:Doctor, Navaru B:Feedback}
21/02/2022 | Started With J-UNIT Testing and Finalizing Front-end Part | 1]FRONT-END: { Ketan A: Admin , Hemalata: Patient , Dhruvi: Doctor SignUp, Varshini: About Us , Bindu: Appointment/Home Page, Naresh: Feedback} 2]BACK-END: {Maneesha: Appointment,Unit testing,Junit Geetha:Discharge, Aravind:Admin, MalkiReddy:Doctor, Navaru B:Feedback} | 1] Morning_Meeting: (9:30 AM TO 10:25 AM) 2] Evening_Meeting: (6.30 PM TO 7:55 PM) | Testing Part Is Almost Done and Front End is Bit lagging. Backend is Almost Finished.
22/02/2022 | Targetting Mostly on FrontEnd Part Today | 1]FRONT-END: { Ketan A: Admin , Hemalata: Patient , Dhruvi: Doctor SignUp, Varshini: About Us , Bindu/Home Page: Appointment, Naresh: Feedback} 2]BACK-END: {Maneesha: Appointment,Unit testing,Junit Geetha:Discharge,JUnit testing, Aravind:Admin, MalkiReddy:Doctor, Navaru B:Feedback} | 1] Morning_Meeting: (9:30 AM TO 10:05 AM) 2] Evening_Meeting: (6.20 PM TO 7:00 PM) | FrontEnd is Going As Planned In Morning And Backend Group Is Focusing on Making it Bug Free For Testing
23/02/2022 | Testing with Data | 1]FRONT-END: { Ketan A: Admin , Hemalata: Patient , Varshini: About Us , Naresh: Feedback} 2]BACK-END: {Maneesha: Appointment,Unit testing,Junit Geetha:Discharge,JUnit testing, Aravind:Admin, Navaru B:Feedback} 3]INTEGRATION-PART: {Dhruvi , Bindu} 4]DOCUMENTATION - {MalkiReddy} | 1] Morning_Meeting: (9:40 AM TO 10:20 AM) 2] Evening_Meeting: (6.30 PM TO 7:10 PM) | Testing Part is Done And Now We Are Working On Remaining Frontend Part .Backend Is Completed Fully!
24/02/2022 | Integrating Project | 1]FRONT-END: { Ketan A: Admin SignUp, Hemalata: Patient , Varshini: About Us , Naresh: Feedback} 2]BACK-END: {Maneesha: Appointment,Unit testing,Junit Geetha:Discharge,JUnit testing, Aravind:Admin, Navaru B:Feedback} 3]INTEGRATION-PART: {Dhruvi , Bindu} 4]DOCUMENTATION - {MalkiReddy} | 1] Morning_Meeting: (9:20 AM TO 10:20 AM) 2] Evening_Meeting: (6.30 PM TO 7:30 PM) | Integration is still in Progress And Some Part in Component is Remaining For Getting Expected Outcomes.
25/02/2022 | Evaluation Day | Everyone Was Present In The Meeting | 1] Afternoon_Meeting: (12:15 PM TO 1:20 PM) 2] Evening_Meeting: (6.05 PM TO 7:00 PM) | SME Team gave modification suggestions
26/02/2022 | Making Modifications | 1]FRONT-END: { Ketan A: Admin,Invoice, Hemalata: Invoice , Naresh: Feedback} 2]BACK-END: {Maneesha: Appointment,Unit testing,Junit Geetha:Discharge,JUnit testing, Aravind:Admin, Navaru B:Feedback} 3]INTEGRATION-PART: {Dhruvi , Bindu, Varshini} 4]DOCUMENTATION - {MalkiReddy} | 1] Morning_Meeting: (9:30 AM TO 10:30 AM) 2] Evening_Meeting: (5.30 PM TO 6:15 PM) | Modifications Like Putting BackSpace Button, Change in the CSS has been made, Discharge Patient Integration Part done.
Note on E17: asus: